## All
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
2011 Crystal | 2025-09-11 | 4 | 36 | Alejandro M S, Gerardo D, Rigoberto Al-B, Rogelio M | 121 | Mobilized and started North side building tree removal and dirt for waterproofing to form paverbase. |  |  | Orlando Trucks | 2 Haul-offs
2011 Crystal | 2025-09-12 | 3 | 27 | Alejandro M S, Gerardo D, Rigoberto Al-B | 121 | Poured North side building tree removal and dirt for waterproofing to form paverbase. | Vulcan | 5
2011 Crystal | 2025-09-12 | 1 | 10 | Rogelio M | 121 | Poured North side building tree removal and dirt for waterproofing to form paverbase. | Vulcan | 5
ARA3A | 2025-09-08 | 6 | 57 | Benito A, Daniel GS, Evaristo A, Leobardo RL, Moises P, Omar S | 124, 122 | Cont with curb at north side of site to tie-in with original bldg | Vulcan | 15 | Chantilly 21a | 1
ARA3A | 2025-09-09 | 6 | 57 | Benito A, Daniel GS, Eric M R, Evaristo A, Leobardo RL, Omar S | 124, 122 | Complete curb at north side road leading to original building. Begin prep of HD either side of road pipe trench | Vulcan | 22
ARA3A | 2025-09-10 |  |  |  | 124, 122 | Pour of west end HD paving at EYD rd at each side of trench box. Prep sidewalk | Vulcan | 9
ARA3A Moorefield | 2025-09-10 | 7 | 67 | Benito A, Daniel GS, Eric M R, Evaristo A, Henry G, Leobardo RL, Omar S
BridgeDist | 2025-09-11 | 2 | 19 | Elvis T, Evaristo A | 118 | Parge over cracks at sidewalk and repairs to permeable pavers at tree pits
Canvas | 2025-09-10 | 2 | 21 | Jose Carlos G, Noe VL
Canvas | 2025-09-12 |  |  |  | D1 | Completed Canvas Clean-up and Work on Yard wifi and weed cleaning.
Canvas, Yard | 2025-09-12 | 1 | 9.5 | Honorio G
Founders 2 | 2025-09-08 | 3 | 28.5 | Honorio G, Rigoberto Al-B, Rogelio M | 121 | Returned to form extension wall in walk alley next to side buidling and started demo of ramp walks.
Founders 2 | 2025-09-09 | 3 | 27 | Honorio G, Rigoberto Al-B, Rogelio M | 121 | Poured extension wall in walk alley buidling and continued demo of ramp walks for Wednesday. | Vulcan | 3
Founders 2 | 2025-09-10 | 4 | 38 | Alejandro M S, Honorio G, Rigoberto Al-B, Rogelio M | 121 | West Broad Street temporary ramps demo and replaced with previous curb and walks. | Vulcan | 8
Founders 2 | 2025-09-11 |  |  |  | 121, 102 | Stripped and rubbed wall and demobilized all material and equipment.
GU Henle | 2025-09-08 | 4 | 38 | Fernando V, Laurentino, Noe VL, Oscar VS | 119 | Started Torndof Lane student lane CO pavers install upper side first and changed elevations.
GU Henle | 2025-09-09 | 4 | 38 | Fernando V, Laurentino, Noe VL, Oscar VS | 119 | Cont'd Torndof Lane student lane CO pavers install upper side first and changed elevations.
GU Henle | 2025-09-10 | 3 | 28.5 | Fernando V, Laurentino, Oscar VS | 119 | Cont'd Torndof Lane student lane CO pavers install upper side first and changed elevations. |  |  | Hanover | Final delivery
GU Henle | 2025-09-11 | 5 | 47.5 | Fernando V, Jose Carlos G, Laurentino, Noe VL, Oscar VS | 119 | Cont'd Torndof Lane student lane CO pavers install heading down middle of road on poured base.
GU Henle | 2025-09-12 | 5 | 47.5 | Fernando V, Jose Carlos G, Laurentino, Noe VL, Oscar VS | 119 | Cont'd Torndof Lane student lane CO pavers install heading down middle of road on poured base.
HanoverSpring | 2025-09-08 | 4 | 38 | Antoine F, Carlos Al-V, Jose P, Rata F | 117 | Begin excavation and rebar for feature wall footers at pool ctyd
HanoverSpring | 2025-09-09 | 6 | 57 | Antoine F, Carlos Al-V, Gaudencio B, Jose P, Moises P, Rata F | 117 | Pour first to feature wall footers with embeds. Ecavcate & prep last, and Fire pit & gas grill footers | Vulcan | 10
HanoverSpring | 2025-09-10 | 5 | 48 | Carlos Al-V, Gaudencio B, Jose P, Moises P, Rata F | 117 | Pour 3rd footer for feature wall and gas and fire pit bases. Begin footer excations at amenities ctyd | Vulcan | 9
HanoverSpring | 2025-09-11 | 5 | 47.5 | Antoine F, Carlos Al-V, Jose P, Moises P, Rata F | 117 | Complete footers at ammeneties ctyd and begin backfill and grade adjacent canopy bases | Vulcan | 13
HanoverSpring | 2025-09-12 | 5 | 47.5 | Antoine F, Carlos Al-V, Jose P, Moises P, Rata F | 117 | Front footer and bases at ammentiese ctyd | Vulcan | 4
HU Plant | 2025-09-12 |  |  |  |  | Concrete For Sorensen | Vulcan | 3
Hyattsville Canvas | 2025-09-10 |  |  |  | 116 | Returned for CO to saw cut down check dam walls rear bio box 9 each for revised calculation for bond.
Kingstowne | 2025-09-11 | 5 | 47.5 | Adalberto T, Gaudencio B, Luis Enrique R, Luis Martin R, Trinidad T | 120, D2 | Excavate and install trench drain at police exit. Prep sidewlak to corner and chipping of damaged conc
Kingstowne | 2025-09-12 | 8 | 78.5 | Adalberto T, Elvis T, Gaudencio B, Julio M, Leobardo RL, Luis Enrique R, Luis Martin R, Trinidad T | 120, 118 | Pour sidewalk along drain and tie in to corner. Cont with CO demo at garage and curb r&r | Vulcan | 7
Moorefield | 2025-09-10 |  |  |  | 124, 22 | Mobilize and begin form of sidewalk at front of building |  |  | Chantilly Pitrun | 1
Moorefield | 2025-09-11 | 7 | 66.5 | Benito A, Daniel GS, Daniel LG, Eric M R, Julio M, Leobardo RL, Omar S | 124, 122 | Pour of sidewalk at main entrance side of front and prep far side. Sawcut jts at ARA | Vulcan | 10
Moorefield | 2025-09-12 | 7 | 66.5 | Benito A, Daniel GS, Daniel LG, Eric M R, Evaristo A, Henry G, Omar S | 124, 122 | Complete sidewalk at front entrance loop. Form & pour walks at SE corner. Excavate & prep sign footer | Vulcan | 8
Rowan | 2025-09-08 | 9 | 85.5 | Adalberto T, Daniel LG, Elvis T, Gaudencio B, Henry G, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | 120, 118 | Cont with curb at periemter of Bldg B | Schuster | 23
Rowan | 2025-09-08 | 9 | 85.5 | Adalberto T, Daniel LG, Elvis T, Gaudencio B, Henry G, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | JMV | Cont with curb at B and form HD exterior pad at corner
Rowan | 2025-09-09 | 8 | 76 | Adalberto T, Daniel LG, Elvis T, Henry G, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | 120, 118 | Cont with curb at perimeter of Bldg B | Schuster | 27
Rowan | 2025-09-09 | 8 | 76 | Adalberto T, Daniel LG, Elvis T, Henry G, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | JMV | Pour HD pad at corner & cont curb
Rowan | 2025-09-10 | 7 | 66.5 | Adalberto T, Daniel LG, Elvis T, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | 120, 118 | Complete curb at perimeter of B and clean up AMA forms | Schuster | 27
Rowan | 2025-09-10 | 7 | 66.5 | Adalberto T, Daniel LG, Elvis T, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | JMV | Curb & pads at bldg b
Rowan | 2025-09-11 |  |  |  | JMV | Cont walks at B and HD pad
Rowan | 2025-09-12 |  |  |  | JMV | Cont wit walk and return to bldg c for curb
Tidal Basin | 2025-09-08 | 6 | 57 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR | 128 | 6:30 am start. Cont'd with wall cap and 3' sidewalk. Cont'd prep of more Exposed Agg walks. | Chaney | 4
Tidal Basin | 2025-09-09 | 6 | 57 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR | 128 | 6:30 am start. Poured next exposed aggregate panels on Seawalls. Prep wall cap and 3' sidewalk. | Chaney | 8
Tidal Basin | 2025-09-10 | 6 | 48 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR | 128 | 6:30 am start. Poured 3' cap stone 3' walks and prepped exposed aggregate panels for Thursday pour. | Chaney | 6
Tidal Basin | 2025-09-11 | 6 | 57 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR | 128 | 6:30 am start. Poured full load of Exposed Aggregate walks and cont'd 3' walk heading West. | Chaney | 9
Tidal Basin | 2025-09-12 | 7 | 66.5 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR, William A | 128 | 6:30 am start. Poured full load of Exposed Aggregate walks and cont'd 3' walk heading West. | Chaney | 6
Tidal Basin | 2025-09-13 | 1 | 4 | Eduardo H | 128 | Water cure refills
Wardman | 2025-09-08 | 14 | 133 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Jose Luis H, Juan G, Miguel A, Misael M, Pablo G, William A | 125, 126 | 125 Calvert St. site curbs and median pour. 125,123 courtyard walks and pool drains. B pavers ski slope. | Vulcan | 13 | Holcim | 18
Wardman | 2025-09-09 | 14 | 133 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Jose Luis H, Juan G, Miguel A, Misael M, Pablo G, William A | 125, 126 | 125 Calvert St. site curbs and median pour. 125,123 courtyard walks and pool drains. B pavers ski slope. | Vulcan | 20 | Holcim | 9
Wardman | 2025-09-10 | 12 | 114 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Juan G, Miguel A, Pablo G, William A | 125, 126 | 125 Calvert St. site curbs and drain pour. 125,123 courtyard walks. B pavers ski slope and above door.. | Vulcan | 10 | Holcim | 9
Wardman | 2025-09-11 | 14 | 130 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Jose Luis H, Juan G, Miguel A, Misael M, Pablo G, William A | 125, 126 | 125 Calvert St. site curbs and drain pour. 125,123 courtyard walks. B pavers ski slope and above door.. | Vulcan | 12 | Holcim | 9
Wardman | 2025-09-12 | 12 | 110.5 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Juan G, Miguel A, Misael M, Pablo G | 125, 126 | 125 Calvert St. site curbs and drain pour. 125,123 courtyard walks. B pavers ski slope and above door.. | Vulcan | 10 | Holcim | 5
Wardman | 2025-09-13 | 9 | 49.5 | Alfonso D, Andres G, Cristobal L, Eliacim R, Jesus L, Juan G, Miguel A, Misael M, Pablo G | 125, 126 | 125 Calvert St side curbs and 125 courtyard walks and saw cuts.

## 2011 Crystal
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
2011 Crystal | 2025-09-11 | 4 | 36 | Alejandro M S, Gerardo D, Rigoberto Al-B, Rogelio M | 121 | Mobilized and started North side building tree removal and dirt for waterproofing to form paverbase. |  |  | Orlando Trucks | 2 Haul-offs
2011 Crystal | 2025-09-12 | 3 | 27 | Alejandro M S, Gerardo D, Rigoberto Al-B | 121 | Poured North side building tree removal and dirt for waterproofing to form paverbase. | Vulcan | 5
2011 Crystal | 2025-09-12 | 1 | 10 | Rogelio M | 121 | Poured North side building tree removal and dirt for waterproofing to form paverbase. | Vulcan | 5

## ARA3A
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
ARA3A | 2025-09-08 | 6 | 57 | Benito A, Daniel GS, Evaristo A, Leobardo RL, Moises P, Omar S | 124, 122 | Cont with curb at north side of site to tie-in with original bldg | Vulcan | 15 | Chantilly 21a | 1
ARA3A | 2025-09-09 | 6 | 57 | Benito A, Daniel GS, Eric M R, Evaristo A, Leobardo RL, Omar S | 124, 122 | Complete curb at north side road leading to original building. Begin prep of HD either side of road pipe trench | Vulcan | 22
ARA3A | 2025-09-10 |  |  |  | 124, 122 | Pour of west end HD paving at EYD rd at each side of trench box. Prep sidewalk | Vulcan | 9

## ARA3A Moorefield
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
ARA3A Moorefield | 2025-09-10 | 7 | 67 | Benito A, Daniel GS, Eric M R, Evaristo A, Henry G, Leobardo RL, Omar S

## BridgeDist
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
BridgeDist | 2025-09-11 | 2 | 19 | Elvis T, Evaristo A | 118 | Parge over cracks at sidewalk and repairs to permeable pavers at tree pits

## Canvas
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
Canvas | 2025-09-10 | 2 | 21 | Jose Carlos G, Noe VL
Canvas | 2025-09-12 |  |  |  | D1 | Completed Canvas Clean-up and Work on Yard wifi and weed cleaning.

## Canvas, Yard
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
Canvas, Yard | 2025-09-12 | 1 | 9.5 | Honorio G

## Founders 2
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
Founders 2 | 2025-09-08 | 3 | 28.5 | Honorio G, Rigoberto Al-B, Rogelio M | 121 | Returned to form extension wall in walk alley next to side buidling and started demo of ramp walks.
Founders 2 | 2025-09-09 | 3 | 27 | Honorio G, Rigoberto Al-B, Rogelio M | 121 | Poured extension wall in walk alley buidling and continued demo of ramp walks for Wednesday. | Vulcan | 3
Founders 2 | 2025-09-10 | 4 | 38 | Alejandro M S, Honorio G, Rigoberto Al-B, Rogelio M | 121 | West Broad Street temporary ramps demo and replaced with previous curb and walks. | Vulcan | 8
Founders 2 | 2025-09-11 |  |  |  | 121, 102 | Stripped and rubbed wall and demobilized all material and equipment.

## GU Henle
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
GU Henle | 2025-09-08 | 4 | 38 | Fernando V, Laurentino, Noe VL, Oscar VS | 119 | Started Torndof Lane student lane CO pavers install upper side first and changed elevations.
GU Henle | 2025-09-09 | 4 | 38 | Fernando V, Laurentino, Noe VL, Oscar VS | 119 | Cont'd Torndof Lane student lane CO pavers install upper side first and changed elevations.
GU Henle | 2025-09-10 | 3 | 28.5 | Fernando V, Laurentino, Oscar VS | 119 | Cont'd Torndof Lane student lane CO pavers install upper side first and changed elevations. |  |  | Hanover | Final delivery
GU Henle | 2025-09-11 | 5 | 47.5 | Fernando V, Jose Carlos G, Laurentino, Noe VL, Oscar VS | 119 | Cont'd Torndof Lane student lane CO pavers install heading down middle of road on poured base.
GU Henle | 2025-09-12 | 5 | 47.5 | Fernando V, Jose Carlos G, Laurentino, Noe VL, Oscar VS | 119 | Cont'd Torndof Lane student lane CO pavers install heading down middle of road on poured base.

## HanoverSpring
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
HanoverSpring | 2025-09-08 | 4 | 38 | Antoine F, Carlos Al-V, Jose P, Rata F | 117 | Begin excavation and rebar for feature wall footers at pool ctyd
HanoverSpring | 2025-09-09 | 6 | 57 | Antoine F, Carlos Al-V, Gaudencio B, Jose P, Moises P, Rata F | 117 | Pour first to feature wall footers with embeds. Ecavcate & prep last, and Fire pit & gas grill footers | Vulcan | 10
HanoverSpring | 2025-09-10 | 5 | 48 | Carlos Al-V, Gaudencio B, Jose P, Moises P, Rata F | 117 | Pour 3rd footer for feature wall and gas and fire pit bases. Begin footer excations at amenities ctyd | Vulcan | 9
HanoverSpring | 2025-09-11 | 5 | 47.5 | Antoine F, Carlos Al-V, Jose P, Moises P, Rata F | 117 | Complete footers at ammeneties ctyd and begin backfill and grade adjacent canopy bases | Vulcan | 13
HanoverSpring | 2025-09-12 | 5 | 47.5 | Antoine F, Carlos Al-V, Jose P, Moises P, Rata F | 117 | Front footer and bases at ammentiese ctyd | Vulcan | 4

## HU Plant
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
HU Plant | 2025-09-12 |  |  |  |  | Concrete For Sorensen | Vulcan | 3

## Hyattsville Canvas
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
Hyattsville Canvas | 2025-09-10 |  |  |  | 116 | Returned for CO to saw cut down check dam walls rear bio box 9 each for revised calculation for bond.

## Kingstowne
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
Kingstowne | 2025-09-11 | 5 | 47.5 | Adalberto T, Gaudencio B, Luis Enrique R, Luis Martin R, Trinidad T | 120, D2 | Excavate and install trench drain at police exit. Prep sidewlak to corner and chipping of damaged conc
Kingstowne | 2025-09-12 | 8 | 78.5 | Adalberto T, Elvis T, Gaudencio B, Julio M, Leobardo RL, Luis Enrique R, Luis Martin R, Trinidad T | 120, 118 | Pour sidewalk along drain and tie in to corner. Cont with CO demo at garage and curb r&r | Vulcan | 7

## Moorefield
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
Moorefield | 2025-09-10 |  |  |  | 124, 22 | Mobilize and begin form of sidewalk at front of building |  |  | Chantilly Pitrun | 1
Moorefield | 2025-09-11 | 7 | 66.5 | Benito A, Daniel GS, Daniel LG, Eric M R, Julio M, Leobardo RL, Omar S | 124, 122 | Pour of sidewalk at main entrance side of front and prep far side. Sawcut jts at ARA | Vulcan | 10
Moorefield | 2025-09-12 | 7 | 66.5 | Benito A, Daniel GS, Daniel LG, Eric M R, Evaristo A, Henry G, Omar S | 124, 122 | Complete sidewalk at front entrance loop. Form & pour walks at SE corner. Excavate & prep sign footer | Vulcan | 8

## Rowan
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
Rowan | 2025-09-08 | 9 | 85.5 | Adalberto T, Daniel LG, Elvis T, Gaudencio B, Henry G, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | 120, 118 | Cont with curb at periemter of Bldg B | Schuster | 23
Rowan | 2025-09-08 | 9 | 85.5 | Adalberto T, Daniel LG, Elvis T, Gaudencio B, Henry G, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | JMV | Cont with curb at B and form HD exterior pad at corner
Rowan | 2025-09-09 | 8 | 76 | Adalberto T, Daniel LG, Elvis T, Henry G, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | 120, 118 | Cont with curb at perimeter of Bldg B | Schuster | 27
Rowan | 2025-09-09 | 8 | 76 | Adalberto T, Daniel LG, Elvis T, Henry G, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | JMV | Pour HD pad at corner & cont curb
Rowan | 2025-09-10 | 7 | 66.5 | Adalberto T, Daniel LG, Elvis T, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | 120, 118 | Complete curb at perimeter of B and clean up AMA forms | Schuster | 27
Rowan | 2025-09-10 | 7 | 66.5 | Adalberto T, Daniel LG, Elvis T, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | JMV | Curb & pads at bldg b
Rowan | 2025-09-11 |  |  |  | JMV | Cont walks at B and HD pad
Rowan | 2025-09-12 |  |  |  | JMV | Cont wit walk and return to bldg c for curb

## Tidal Basin
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
Tidal Basin | 2025-09-08 | 6 | 57 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR | 128 | 6:30 am start. Cont'd with wall cap and 3' sidewalk. Cont'd prep of more Exposed Agg walks. | Chaney | 4
Tidal Basin | 2025-09-09 | 6 | 57 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR | 128 | 6:30 am start. Poured next exposed aggregate panels on Seawalls. Prep wall cap and 3' sidewalk. | Chaney | 8
Tidal Basin | 2025-09-10 | 6 | 48 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR | 128 | 6:30 am start. Poured 3' cap stone 3' walks and prepped exposed aggregate panels for Thursday pour. | Chaney | 6
Tidal Basin | 2025-09-11 | 6 | 57 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR | 128 | 6:30 am start. Poured full load of Exposed Aggregate walks and cont'd 3' walk heading West. | Chaney | 9
Tidal Basin | 2025-09-12 | 7 | 66.5 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR, William A | 128 | 6:30 am start. Poured full load of Exposed Aggregate walks and cont'd 3' walk heading West. | Chaney | 6
Tidal Basin | 2025-09-13 | 1 | 4 | Eduardo H | 128 | Water cure refills

## Wardman
Job | Date | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
Wardman | 2025-09-08 | 14 | 133 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Jose Luis H, Juan G, Miguel A, Misael M, Pablo G, William A | 125, 126 | 125 Calvert St. site curbs and median pour. 125,123 courtyard walks and pool drains. B pavers ski slope. | Vulcan | 13 | Holcim | 18
Wardman | 2025-09-09 | 14 | 133 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Jose Luis H, Juan G, Miguel A, Misael M, Pablo G, William A | 125, 126 | 125 Calvert St. site curbs and median pour. 125,123 courtyard walks and pool drains. B pavers ski slope. | Vulcan | 20 | Holcim | 9
Wardman | 2025-09-10 | 12 | 114 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Juan G, Miguel A, Pablo G, William A | 125, 126 | 125 Calvert St. site curbs and drain pour. 125,123 courtyard walks. B pavers ski slope and above door.. | Vulcan | 10 | Holcim | 9
Wardman | 2025-09-11 | 14 | 130 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Jose Luis H, Juan G, Miguel A, Misael M, Pablo G, William A | 125, 126 | 125 Calvert St. site curbs and drain pour. 125,123 courtyard walks. B pavers ski slope and above door.. | Vulcan | 12 | Holcim | 9
Wardman | 2025-09-12 | 12 | 110.5 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Juan G, Miguel A, Misael M, Pablo G | 125, 126 | 125 Calvert St. site curbs and drain pour. 125,123 courtyard walks. B pavers ski slope and above door.. | Vulcan | 10 | Holcim | 5
Wardman | 2025-09-13 | 9 | 49.5 | Alfonso D, Andres G, Cristobal L, Eliacim R, Jesus L, Juan G, Miguel A, Misael M, Pablo G | 125, 126 | 125 Calvert St side curbs and 125 courtyard walks and saw cuts.