## Sheet1
Date | Job | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds
2025-09-08 | Tidal Basin | 128 | 6:30 am start. Cont'd with wall cap and 3' sidewalk. Cont'd prep of more Exposed Agg walks. | Chaney | 4
2025-09-09 | Tidal Basin | 128 | 6:30 am start. Poured next exposed aggregate panels on Seawalls. Prep wall cap and 3' sidewalk. | Chaney | 8
2025-09-10 | Tidal Basin | 128 | 6:30 am start. Poured 3' cap stone 3' walks and prepped exposed aggregate panels for Thursday pour. | Chaney | 6
2025-09-11 | Tidal Basin | 128 | 6:30 am start. Poured full load of Exposed Aggregate walks and cont'd 3' walk heading West. | Chaney | 9
2025-09-12 | Tidal Basin | 128 | 6:30 am start. Poured full load of Exposed Aggregate walks and cont'd 3' walk heading West. | Chaney | 6
2025-09-13 | Tidal Basin | 128 | Water cure refills
2025-09-08 | Wardman | 125, 126 | 125 Calvert St. site curbs and median pour. 125,123 courtyard walks and pool drains. B pavers ski slope. | Vulcan | 13 | Holcim | 18
2025-09-09 | Wardman | 125, 126 | 125 Calvert St. site curbs and median pour. 125,123 courtyard walks and pool drains. B pavers ski slope. | Vulcan | 20 | Holcim | 9
2025-09-10 | Wardman | 125, 126 | 125 Calvert St. site curbs and drain pour. 125,123 courtyard walks. B pavers ski slope and above door.. | Vulcan | 10 | Holcim | 9
2025-09-11 | Wardman | 125, 126 | 125 Calvert St. site curbs and drain pour. 125,123 courtyard walks. B pavers ski slope and above door.. | Vulcan | 12 | Holcim | 9
2025-09-12 | Wardman | 125, 126 | 125 Calvert St. site curbs and drain pour. 125,123 courtyard walks. B pavers ski slope and above door.. | Vulcan | 10 | Holcim | 5
2025-09-13 | Wardman | 125, 126 | 125 Calvert St side curbs and 125 courtyard walks and saw cuts.
2025-09-08 | Founders 2 | 121 | Returned to form extension wall in walk alley next to side buidling and started demo of ramp walks.
2025-09-09 | Founders 2 | 121 | Poured extension wall in walk alley buidling and continued demo of ramp walks for Wednesday. | Vulcan | 3
2025-09-10 | Founders 2 | 121 | West Broad Street temporary ramps demo and replaced with previous curb and walks. | Vulcan | 8
2025-09-11 | Founders 2 | 121, 102 | Stripped and rubbed wall and demobilized all material and equipment.
2025-09-12 | Canvas | D1 | Completed Canvas Clean-up and Work on Yard wifi and weed cleaning.
2025-09-08 | GU Henle | 119 | Started Torndof Lane student lane CO pavers install upper side first and changed elevations.
2025-09-09 | GU Henle | 119 | Cont'd Torndof Lane student lane CO pavers install upper side first and changed elevations.
2025-09-10 | GU Henle | 119 | Cont'd Torndof Lane student lane CO pavers install upper side first and changed elevations. |  |  | Hanover | Final delivery
2025-09-11 | GU Henle | 119 | Cont'd Torndof Lane student lane CO pavers install heading down middle of road on poured base.
2025-09-12 | GU Henle | 119 | Cont'd Torndof Lane student lane CO pavers install heading down middle of road on poured base.
2025-09-10 | Hyattsville Canvas | 116 | Returned for CO to saw cut down check dam walls rear bio box 9 each for revised calculation for bond.
2025-09-11 | 2011 Crystal | 121 | Mobilized and started North side building tree removal and dirt for waterproofing to form paverbase. |  |  | Orlando Trucks | 2 Haul-offs
2025-09-12 | 2011 Crystal | 121 | Poured North side building tree removal and dirt for waterproofing to form paverbase. | Vulcan | 5
2025-09-10 | Moorefield | 124, 22 | Mobilize and begin form of sidewalk at front of building |  |  | Chantilly Pitrun | 1
2025-09-11 | BridgeDist | 118 | Parge over cracks at sidewalk and repairs to permeable pavers at tree pits
2025-09-12 | HU Plant |  | Concrete For Sorensen | Vulcan | 3
2025-09-08 | ARA3A | 124, 122 | Cont with curb at north side of site to tie-in with original bldg | Vulcan | 15 | Chantilly 21a | 1
2025-09-09 | ARA3A | 124, 122 | Complete curb at north side road leading to original building. Begin prep of HD either side of road pipe trench | Vulcan | 22
2025-09-10 | ARA3A | 124, 122 | Pour of west end HD paving at EYD rd at each side of trench box. Prep sidewalk | Vulcan | 9
2025-09-11 | Moorefield | 124, 122 | Pour of sidewalk at main entrance side of front and prep far side. Sawcut jts at ARA | Vulcan | 10
2025-09-12 | Moorefield | 124, 122 | Complete sidewalk at front entrance loop. Form & pour walks at SE corner. Excavate & prep sign footer | Vulcan | 8
2025-09-08 | HanoverSpring | 117 | Begin excavation and rebar for feature wall footers at pool ctyd
2025-09-09 | HanoverSpring | 117 | Pour first to feature wall footers with embeds. Ecavcate & prep last, and Fire pit & gas grill footers | Vulcan | 10
2025-09-10 | HanoverSpring | 117 | Pour 3rd footer for feature wall and gas and fire pit bases. Begin footer excations at amenities ctyd | Vulcan | 9
2025-09-11 | HanoverSpring | 117 | Complete footers at ammeneties ctyd and begin backfill and grade adjacent canopy bases | Vulcan | 13
2025-09-12 | HanoverSpring | 117 | Front footer and bases at ammentiese ctyd | Vulcan | 4
2025-09-08 | Rowan | 120, 118 | Cont with curb at periemter of Bldg B | Schuster | 23
2025-09-09 | Rowan | 120, 118 | Cont with curb at perimeter of Bldg B | Schuster | 27
2025-09-10 | Rowan | 120, 118 | Complete curb at perimeter of B and clean up AMA forms | Schuster | 27
2025-09-11 | Kingstowne | 120, D2 | Excavate and install trench drain at police exit. Prep sidewlak to corner and chipping of damaged conc
2025-09-12 | Kingstowne | 120, 118 | Pour sidewalk along drain and tie in to corner. Cont with CO demo at garage and curb r&r | Vulcan | 7
2025-09-08 | Rowan | JMV | Cont with curb at B and form HD exterior pad at corner
2025-09-09 | Rowan | JMV | Pour HD pad at corner & cont curb
2025-09-10 | Rowan | JMV | Curb & pads at bldg b
2025-09-11 | Rowan | JMV | Cont walks at B and HD pad
2025-09-12 | Rowan | JMV | Cont wit walk and return to bldg c for curb