## Sheet1
Date | Job | EmployeeCount | TotalHours | Employees | Truck(s) | Description | Concrete | Concrete Yds | Stone | Stone Lds | Job_timesheet | Job_norm | Job_job
2025-09-08 | ARA3A | 5 | 47.5 | Benito A, Daniel GS, Evaristo A, Leobardo RL, Omar S | 124, 122 | Cont with curb at north side of site to tie-in with original bldg | Vulcan | 15 | Chantilly 21a | 1 | ARA3A | ARA3A | ARA3A
2025-09-08 | Column8 | 1 | 4 | Column1 | [6 empty] | Column8 | Column8
2025-09-08 | Founders 2 | 3 | 28.5 | Honorio G, Rigoberto Al-B, Rogelio M | 121 | Returned to form extension wall in walk alley next to side buidling and started demo of ramp walks. |  |  |  |  | Founders 2 | Founders 2 | Founders 2
2025-09-08 | GU Henle | 4 | 38 | Fernando V, Laurentino, Noe VL, Oscar VS | 119 | Started Torndof Lane student lane CO pavers install upper side first and changed elevations. |  |  |  |  | GU Henle | GU Henle | GU Henle
2025-09-08 | HanoverSpring | 6 | 57 | Antoine F, Carlos Al-V, Gaudencio B, Jose P, Moises P, Rata F | 117 | Begin excavation and rebar for feature wall footers at pool ctyd |  |  |  |  | HanoverSpring | HanoverSpring | HanoverSpring
2025-09-08 | Rowan | 8 | 76 | Adalberto T, Daniel LG, Elvis T, Henry G, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | 120, 118 | Cont with curb at periemter of Bldg B | Schuster | 23 |  |  | Rowan | Rowan | Rowan
2025-09-08 | Rowan | 8 | 76 | Adalberto T, Daniel LG, Elvis T, Henry G, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | JMV | Cont with curb at B and form HD exterior pad at corner |  |  |  |  | Rowan | Rowan | Rowan
2025-09-08 | Tidal Basin | 6 | 57 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR | 128 | 6:30 am start. Cont'd with wall cap and 3' sidewalk. Cont'd prep of more Exposed Agg walks. | Chaney | 4 |  |  | Tidal Basin | Tidal Basin | Tidal Basin
2025-09-08 | Wardman | 14 | 133 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Jose Luis H, Juan G, Miguel A, Misael M, Pablo G, William A | 125, 126 | 125 Calvert St. site curbs and median pour. 125,123 courtyard walks and pool drains. B pavers ski slope. | Vulcan | 13 | Holcim | 18 | Wardman | Wardman | Wardman
2025-09-09 | ARA3A |  |  |  | 124, 122 | Complete curb at north side road leading to original building. Begin prep of HD either side of road pipe trench | Vulcan | 22 |  |  |  | ARA3A | ARA3A
2025-09-09 | ARA3A Moorefield | 7 | 66.5 | Benito A, Daniel GS, Eric M R, Evaristo A, Henry G, Leobardo RL, Omar S | [6 empty] | ARA3A Moorefield | ARA3A Moorefield
2025-09-09 | Canvas | 1 | 9.5 | Noe VL | [6 empty] | Canvas | Canvas
2025-09-09 | Column13 | 1 | 9 | Column1 | [6 empty] | Column13 | Column13
2025-09-09 | Founders 2 | 3 | 27 | Honorio G, Rigoberto Al-B, Rogelio M | 121 | Poured extension wall in walk alley buidling and continued demo of ramp walks for Wednesday. | Vulcan | 3 |  |  | Founders 2 | Founders 2 | Founders 2
2025-09-09 | GU Henle | 3 | 28.5 | Fernando V, Laurentino, Oscar VS | 119 | Cont'd Torndof Lane student lane CO pavers install upper side first and changed elevations. |  |  |  |  | GU Henle | GU Henle | GU Henle
2025-09-09 | HanoverSpring | 5 | 47.5 | Carlos Al-V, Gaudencio B, Jose P, Moises P, Rata F | 117 | Pour first to feature wall footers with embeds. Ecavcate & prep last, and Fire pit & gas grill footers | Vulcan | 10 |  |  | HanoverSpring | HanoverSpring | HanoverSpring
2025-09-09 | Rowan | 7 | 66.5 | Adalberto T, Daniel LG, Elvis T, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | 120, 118 | Cont with curb at perimeter of Bldg B | Schuster | 27 |  |  | Rowan | Rowan | Rowan
2025-09-09 | Rowan | 7 | 66.5 | Adalberto T, Daniel LG, Elvis T, Julio M, Luis Enrique R, Luis Martin R, Trinidad T | JMV | Pour HD pad at corner & cont curb |  |  |  |  | Rowan | Rowan | Rowan
2025-09-09 | Tidal Basin | 6 | 57 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR | 128 | 6:30 am start. Poured next exposed aggregate panels on Seawalls. Prep wall cap and 3' sidewalk. | Chaney | 8 |  |  | Tidal Basin | Tidal Basin | Tidal Basin
2025-09-09 | Wardman | 12 | 114 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Juan G, Miguel A, Pablo G, William A | 125, 126 | 125 Calvert St. site curbs and median pour. 125,123 courtyard walks and pool drains. B pavers ski slope. | Vulcan | 20 | Holcim | 9 | Wardman | Wardman | Wardman
2025-09-10 | 2011 Crystal | 3 | 28.5 | Alejandro M S, Rigoberto Al-B, Rogelio M | [6 empty] | 2011 Crystal | 2011 Crystal
2025-09-10 | ARA3A |  |  |  | 124, 122 | Pour of west end HD paving at EYD rd at each side of trench box. Prep sidewalk | Vulcan | 9 |  |  |  | ARA3A | ARA3A
2025-09-10 | BridgeDist | 2 | 19 | Elvis T, Evaristo A | [6 empty] | BridgeDist | BridgeDist
2025-09-10 | Column18 | 1 | 14 | Column1 | [6 empty] | Column18 | Column18
2025-09-10 | Founders 2 |  |  |  | 121 | West Broad Street temporary ramps demo and replaced with previous curb and walks. | Vulcan | 8 |  |  |  | Founders 2 | Founders 2
2025-09-10 | GU Henle | 5 | 49.5 | Fernando V, Jose Carlos G, Laurentino, Noe VL, Oscar VS | 119 | Cont'd Torndof Lane student lane CO pavers install upper side first and changed elevations. |  |  | Hanover | Final delivery | GU Henle | GU Henle | GU Henle
2025-09-10 | HanoverSpring | 4 | 38 | Carlos Al-V, Jose P, Moises P, Rata F | 117 | Pour 3rd footer for feature wall and gas and fire pit bases. Begin footer excations at amenities ctyd | Vulcan | 9 |  |  | HanoverSpring | HanoverSpring | HanoverSpring
2025-09-10 | Hyattsville Canvas |  |  |  | 116 | Returned for CO to saw cut down check dam walls rear bio box 9 each for revised calculation for bond. | [5 empty] | Hyattsville Canvas | Hyattsville Canvas
2025-09-10 | Kingstowne | 5 | 48 | Adalberto T, Gaudencio B, Luis Enrique R, Luis Martin R, Trinidad T | [6 empty] | Kingstowne | Kingstowne
2025-09-10 | Moorefield |  |  |  | 124, 22 | Mobilize and begin form of sidewalk at front of building |  |  | Chantilly Pitrun | 1 |  | Moorefield | Moorefield
2025-09-10 | Moorfield | 7 | 67 | Benito A, Daniel GS, Daniel LG, Eric M R, Julio M, Leobardo RL, Omar S | [6 empty] | Moorfield | Moorfield
2025-09-10 | Rowan |  |  |  | 120, 118 | Complete curb at perimeter of B and clean up AMA forms | Schuster | 27 |  |  |  | Rowan | Rowan
2025-09-10 | Rowan |  |  |  | JMV | Curb & pads at bldg b | [5 empty] | Rowan | Rowan
2025-09-10 | Tidal Basin | 6 | 48 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR | 128 | 6:30 am start. Poured 3' cap stone 3' walks and prepped exposed aggregate panels for Thursday pour. | Chaney | 6 |  |  | Tidal Basin | Tidal Basin | Tidal Basin
2025-09-10 | Wardman | 12 | 114 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Juan G, Miguel A, Pablo G, William A | 125, 126 | 125 Calvert St. site curbs and drain pour. 125,123 courtyard walks. B pavers ski slope and above door.. | Vulcan | 10 | Holcim | 9 | Wardman | Wardman | Wardman
2025-09-11 | 2011 Crystal | 3 | 27 | Alejandro M S, Gerardo D, Rigoberto Al-B | 121 | Mobilized and started North side building tree removal and dirt for waterproofing to form paverbase. |  |  | Orlando Trucks | 2 Haul-offs | 2011 Crystal | 2011 Crystal | 2011 Crystal
2025-09-11 | 2011 Crystal Yard | 1 | 9 | Rogelio M | [6 empty] | 2011 Crystal Yard | 2011 Crystal Yard
2025-09-11 | BridgeDist |  |  |  | 118 | Parge over cracks at sidewalk and repairs to permeable pavers at tree pits | [5 empty] | BridgeDist | BridgeDist
2025-09-11 | Column23 | 1 | 19 | Column1 | [6 empty] | Column23 | Column23
2025-09-11 | Founders 2 |  |  |  | 121, 102 | Stripped and rubbed wall and demobilized all material and equipment. | [5 empty] | Founders 2 | Founders 2
2025-09-11 | GU Henle | 5 | 47.5 | Fernando V, Jose Carlos G, Laurentino, Noe VL, Oscar VS | 119 | Cont'd Torndof Lane student lane CO pavers install heading down middle of road on poured base. |  |  |  |  | GU Henle | GU Henle | GU Henle
2025-09-11 | HanoverSpring | 5 | 47.5 | Antoine F, Carlos Al-V, Jose P, Moises P, Rata F | 117 | Complete footers at ammeneties ctyd and begin backfill and grade adjacent canopy bases | Vulcan | 13 |  |  | HanoverSpring | HanoverSpring | HanoverSpring
2025-09-11 | Kingstowne | 8 | 76 | Adalberto T, Elvis T, Gaudencio B, Julio M, Leobardo RL, Luis Enrique R, Luis Martin R, Trinidad T | 120, D2 | Excavate and install trench drain at police exit. Prep sidewlak to corner and chipping of damaged conc |  |  |  |  | Kingstowne | Kingstowne | Kingstowne
2025-09-11 | Moorefield | 6 | 57 | Benito A, Daniel GS, Daniel LG, Eric M R, Evaristo A, Omar S | 124, 122 | Pour of sidewalk at main entrance side of front and prep far side. Sawcut jts at ARA | Vulcan | 10 |  |  | Moorefield | Moorefield | Moorefield
2025-09-11 | Rowan |  |  |  | JMV | Cont walks at B and HD pad | [5 empty] | Rowan | Rowan
2025-09-11 | Tidal Basin | 7 | 66.5 | Alberto R, Danis BA, Eduardo H, Feliciano R, Isidro M, Juan HR, William A | 128 | 6:30 am start. Poured full load of Exposed Aggregate walks and cont'd 3' walk heading West. | Chaney | 9 |  |  | Tidal Basin | Tidal Basin | Tidal Basin
2025-09-11 | Wardman | 12 | 111 | Alfonso D, Andres G, Benny S, Carlos G, Cristobal L, Diego R, Eliacim R, Jesus L, Juan G, Miguel A, Misael M, Pablo G | 125, 126 | 125 Calvert St. site curbs and drain pour. 125,123 courtyard walks. B pavers ski slope and above door.. | Vulcan | 12 | Holcim | 9 | Wardman | Wardman | Wardman
2025-09-12 | 2011 Crystal |  |  |  | 121 | Poured North side building tree removal and dirt for waterproofing to form paverbase. | Vulcan | 5 |  |  |  | 2011 Crystal | 2011 Crystal
2025-09-12 | Canvas |  |  |  | D1 | Completed Canvas Clean-up and Work on Yard wifi and weed cleaning. | [5 empty] | Canvas | Canvas
2025-09-12 | Column28 | 1 | 24 | Column1 | [6 empty] | Column28 | Column28
2025-09-12 | GU Henle |  |  |  | 119 | Cont'd Torndof Lane student lane CO pavers install heading down middle of road on poured base. | [5 empty] | GU Henle | GU Henle
2025-09-12 | HU Plant |  |  |  |  | Concrete For Sorensen | Vulcan | 3 |  |  |  | HU Plant | HU Plant
2025-09-12 | HanoverSpring |  |  |  | 117 | Front footer and bases at ammentiese ctyd | Vulcan | 4 |  |  |  | HanoverSpring | HanoverSpring
2025-09-12 | Kingstowne |  |  |  | 120, 118 | Pour sidewalk along drain and tie in to corner. Cont with CO demo at garage and curb r&r | Vulcan | 7 |  |  |  | Kingstowne | Kingstowne
2025-09-12 | Moorefield |  |  |  | 124, 122 | Complete sidewalk at front entrance loop. Form & pour walks at SE corner. Excavate & prep sign footer | Vulcan | 8 |  |  |  | Moorefield | Moorefield
2025-09-12 | Rowan |  |  |  | JMV | Cont wit walk and return to bldg c for curb | [5 empty] | Rowan | Rowan
2025-09-12 | Tidal Basin | 1 | 9.5 | Eduardo H | 128 | 6:30 am start. Poured full load of Exposed Aggregate walks and cont'd 3' walk heading West. | Chaney | 6 |  |  | Tidal Basin | Tidal Basin | Tidal Basin
2025-09-12 | Wardman | 9 | 82 | Alfonso D, Andres G, Cristobal L, Eliacim R, Jesus L, Juan G, Miguel A, Misael M, Pablo G | 125, 126 | 125 Calvert St. site curbs and drain pour. 125,123 courtyard walks. B pavers ski slope and above door.. | Vulcan | 10 | Holcim | 5 | Wardman | Wardman | Wardman
2025-09-13 | Column28 | 1 | 29 | Column1 | [6 empty] | Column28 | Column28
2025-09-13 | Tidal Basin | 1 | 4 | Eduardo H | 128 | Water cure refills |  |  |  |  | Tidal Basin | Tidal Basin | Tidal Basin
2025-09-13 | Wardman | 9 | 49.5 | Alfonso D, Andres G, Cristobal L, Eliacim R, Jesus L, Juan G, Miguel A, Misael M, Pablo G | 125, 126 | 125 Calvert St side curbs and 125 courtyard walks and saw cuts. |  |  |  |  | Wardman | Wardman | Wardman